## Sheet1
Time Plan Grand Opening Outlet KOPO
TO DO | PIC | Km | Jm | Sb | M | Sn | Sl | Rb | Km | Jm | Sb | M | Sn | Sl | Rb | Km | Jm | Sb | M | Sn | Sl | Rb | Km | Jm | Sb | M | Sn | Sl | Rb | Km | Jm | Sb | M | Sn | Sl | Rb | Km | Jm | Sb
|  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Rekruitment RM | HR | bar: Km 15 to Jm 16
Rekruitment Crew | HR | Jm 16: crew kopo; Km 22: crew b/u
Training Team Kopo (Fundamental) | Training | bar: Sn 19 to Sl 20; Sn 26 to Sl 27
Meeting Koodinasi Team Kopo | AM | bar: Rb 28
Training Team Kopo (SOC di Cisitu) | AM & Ilyas | Km 22: running team KOPO di Cisitu dg pengawasan RM & AM
Fix Crew Dream Team KOPO | bisa pinjem dr store lama | Sb 8: Dream Team
Order Bahan Baku KOPO | bar: Sl 11 to Rb 12
Hand Over Building & ME | Countration, ME, Ops | bar: M 16
Test Equipment | ME & Ops | bar: Sn 17
Loading Bahan Baku | Ops | bar: Sn 17
Briefing & test Running | Team Opening & Ops | bar: Sl 18
Detail Cleaning & Preparation | Team Opening & Ops | bar: Sl 18
Soft Opening | Team Opening & Ops | bar: Rb 19 to Jm 21
- Tamu Relasi & Share Holder | bar: Rb 19 to Jm 21
- Undang Yatim Piatu & Tumpengan | bar: Rb 19 to Jm 21
Grand Opening | Team Opening & Ops | bar: Sb 22
Running Operasional
[7 empty] | Dead Line | team kopo | [19 empty] | RENOV Done